## Budget Summary
P1 LMS+SMS — Budget & Resource Plan v1.0
Lighthouse Global School System ¦ Internal — Consultant Use Only
Category | PKR | USD (@ 278) | % of Total
Development + Design + Lead hands-on (all modules) | 2057944 | 7402.6763 | 26.07%
Combined Lead — PM / Architecture / QA overhead | 1332173 | 4791.9892 | 16.87%
Security Consultant (2 engagements) | 1200000 | 4316.5468 | 15.2%
Infrastructure during build (AWS + VPS) | 1151710 | 4142.8417 | 14.59%
AI development tooling — Claude Code 7 seats | 1123557 | 4041.5719 | 14.23%
Subtotal (before contingency) | 6865384 | 24695.6259
Contingency (15%) | 1029807.6 | 3704.3439 | 15%
TOTAL PROJECT BUDGET | 7895191.6 | 28399.9698

## Hours Matrix
Hours by Module by Role (AI-Adjusted)
Module | Backend Hrs | Frontend Hrs | UI/UX Hrs | Lead Hrs | Module Total PKR
M01 — Admissions | 66 | 75 | 10 | 9 | 116758
M02 — Live Online Classes | 90 | 120 | 13 | 32 | 210858
M03 — Assignment | 60 | 68 | 9 | 8 | 105588
M04 — Exam | 98 | 113 | 15 | 12 | 171725
M05 — Gradebook | 55 | 62 | 8 | 7 | 95712
M06 — Attendance | 41 | 47 | 6 | 5 | 71431
M07 — Timetable/Scheduling | 66 | 75 | 10 | 9 | 116758
M08 — Fee Management | 71 | 81 | 11 | 9 | 124575
M09 — Accounting | 119 | 85 | 12 | 9 | 158919
M10 — HR Staff Management | 56 | 40 | 6 | 4 | 74548
M11 — Payroll | 77 | 55 | 8 | 6 | 103358
M12 — Library Management | 38 | 44 | 6 | 5 | 67549
M13 — Communication | 49 | 57 | 8 | 6 | 86536
M14 — Psychological Assessment | 87 | 100 | 13 | 11 | 152738
M15 — Transport | 25 | 28 | 4 | 3 | 43268
M16 — Cognia Evidence Management | 35 | 25 | 4 | 3 | 47797
M17 — Platform Administration | 70 | 49 | 7 | 5 | 92188
M18 — User & Role Management | 77 | 55 | 8 | 6 | 103358
M19 — Reports & Analytics | 49 | 57 | 8 | 6 | 86536
M20 — Settings & Configuration | 29 | 20 | 3 | 2 | 37921
TOTAL | 1258 | 1256 | 169 | 157 | 2068121

## Monthly OpEx (Post-Launch)
Monthly Operating Costs Post-Launch
Cost Category | Monthly (USD) | Monthly (PKR @ 278)
AWS Production infrastructure | 2300 | 639400
AI API costs (moderate adoption) | 21 | 5838
SMS/Email/WhatsApp gateway fees | 150 | 41700
SaaS tooling (CI/CD, monitoring, PM) | 200 | 55600
Security Consultant (amortised) | (PKR 100,000/mo — see PKR col) | 100000
TOTAL MONTHLY OPEX | 2671 | 842538