## Milestone Schedule
P1 LMS+SMS — Project Timeline v1.0
Lighthouse Global School System ¦ Internal — Consultant Use Only
Milestone | Deliverable | Target Date | Owner | Acceptance Criteria | Status
M1 — Kickoff | Scope Lock signed; team onboarded; AWS/VPS provisioned; all 9 third-party integration accounts requested | 6 Jul 2026 | Combined Lead | Scope Lock Agreement signature on file | 🔵 Upcoming
M2 — Foundation Complete | Auth/RBAC live for all 8 roles; tenant isolation verified; CI/CD pipeline live | 18 Jul 2026 | Combined Lead | Auth test suite passes all 8 roles; cross-tenant query test blocked | ⬜ Not Started
M3 — Core Academic Complete | M01–M07 in QA | 28 Aug 2026 | Backend Lead, Frontend Lead | All M01–M07 acceptance criteria pass in QA | ⬜ Not Started
M4 — Finance & Ops Complete | M08–M12, M15 in QA | 25 Sep 2026 | Backend Lead, Frontend Lead | All M08–M12, M15 criteria pass; double-entry balance verified | ⬜ Not Started
M5 — Specialised Complete | M13, M14, M16, M19 in QA | 13 Oct 2026 | Backend Lead, Frontend Lead | All M13/M14/M16/M19 criteria pass; BR-031/032 visibility verified | ⬜ Not Started
M6 — Feature Complete / Code Freeze | All 20 modules merged to main; deployed to UAT | 16 Oct 2026 | Combined Lead | UAT env matches Part 11.2; no Sev-1/Sev-2 defects | ⬜ Not Started
M7 — Penetration Test | Security Consultant engagement #1 complete | 24 Oct 2026 | Security Consultant | Pen test report delivered; all Critical/High findings remediated | ⬜ Not Started
M8 — UAT Sign-Off | Client acceptance of UAT | 14 Nov 2026 | Project Sponsor | Signed UAT document; all Part 15.7 criteria marked Pass; zero Sev-1/2 | ⬜ Not Started
M9 — Go-Live Readiness | Pre-launch checklist complete | 25 Nov 2026 | Combined Lead | Every item in Part 14.6 checklist checked off | ⬜ Not Started
M10 — GO-LIVE | Production cutover | 30 Nov 2026 | Combined Lead | Production serving live traffic; rollback on standby 72h | ⬜ Not Started

## Phase Plan
Development Phase Plan
Phase | Duration | Start | End | Key Modules
Phase 1 — Foundation & Platform Core | 1.8 weeks | 6 Jul 2026 | 18 Jul 2026 | M17, M18, M20
Phase 2 — Core Academic | 5.8 weeks | 19 Jul 2026 | 28 Aug 2026 | M01, M02, M03, M04, M05, M06, M07
Phase 3 — Finance & Operations | 4.0 weeks | 29 Aug 2026 | 25 Sep 2026 | M08, M09, M10, M11, M12, M15
Phase 4 — Specialised & Compliance | 2.5 weeks | 26 Sep 2026 | 13 Oct 2026 | M13, M14, M16, M19
Phase 5 — Integration, UAT & Hardening | 5.1 weeks | 14 Oct 2026 | 18 Nov 2026 | All modules (cross-cutting)
Schedule Buffer | 1.6 weeks | 19 Nov 2026 | 29 Nov 2026 | —
GO-LIVE | — | 30 Nov 2026 | — | All 20 modules