## Risk Register
P1 LMS+SMS — Risk Register v1.0 — Live Tracker
Lighthouse Global School System ¦ Update Status column as risks are reviewed. Risk Score = Probability × Impact.
ID | Category | Risk Description | Probability (1-5) | Impact (1-5) | Score (P×I) | Mitigation | Contingency | Owner | Review Date
RISK-T-001 | Technical | React Native proctoring screen fails to enforce full-screen lock on iOS/Android | 3 | 4 | 12 | Part 9.1 native-module fallback defined; build proctoring screen natively if RN fails | Descope mobile proctoring for v1.0; deliver as web-only | Frontend Lead | Phase 2 completion (28 Aug 2026)
RISK-T-002 | Technical | JazzCash/Easypaisa integration more complex than estimated; extends Phase 3 | 4 | 3 | 12 | Backend Lead (not intern) assigned; integration spike in Phase 2 final week | Defer JazzCash/Easypaisa to v1.1; deliver Stripe/PayPal only at Go-Live | Backend Lead | Start of Phase 3 (29 Aug 2026)
RISK-T-003 | Technical | AWS performance at load does not meet 2,000 concurrent user NFR target | 2 | 4 | 8 | Performance tests in Phase 5 against UAT before Go-Live | Scale up AWS instance types or add ElastiCache; funded from contingency | Backend Lead | Phase 5 perf test (Oct 2026)
RISK-T-004 | Technical | Multi-tenant data isolation gap — query leaks data across school tenants | 2 | 5 | 10 | Tenant isolation tested as first-class concern; pen test includes cross-tenant test | Immediate: offline affected endpoint; patch; re-test; notify affected tenants | Combined Lead | Pen test (M7, 24 Oct 2026)
RISK-T-005 | Technical | Zoom/Meet/Teams API credentials not provided before Phase 2 Live Classes module | 3 | 3 | 9 | Jitsi self-hosted always available as fallback; dev proceeds against Jitsi | Third-party adaptors built in Phase 5 parallel track once credentials arrive | Combined Lead | Kickoff (M1, 6 Jul 2026)
RISK-B-001 | Business | Scope creep — client requests additions after Scope Lock signature | 4 | 3 | 12 | Part 17.1 Change Request Process: no dev starts without signed CR approval | Any approved CR shifts Go-Live date; does not compress earlier phases | Combined Lead | Every Phase review
RISK-B-002 | Business | Key client stakeholder changes mid-project; previously agreed requirements re-opened | 2 | 4 | 8 | Scope Lock signed at org level not individual; agreement binds the organisation | Offer structured discovery session; process changes as formal CRs | Project Sponsor + Combined Lead | Every Phase milestone
RISK-B-003 | Business | UAT participant availability insufficient (school not yet at student capacity) | 3 | 2 | 6 | Confirm UAT participants at Kickoff; identify alternates for each role | Admin staff role-play student/parent UAT scenarios using scripts | Project Sponsor | Kickoff (M1, 6 Jul 2026)
RISK-B-004 | Business | Cambridge Assessment API access unavailable before Phase 2 Exam module | 3 | 3 | 9 | Exam module built without Cambridge API; Cambridge format added when access arrives | Deliver Exam module without Cambridge-specific paper format; v1.1 patch | Combined Lead + Project Sponsor | Start of Phase 2 (19 Jul 2026)
RISK-B-005 | Business | Budget overrun beyond 15% contingency | 2 | 4 | 8 | 15% contingency funded; on-demand outsourced capacity as alternative to spending reserve | Scope-down lowest-priority modules (M15 Transport, M12 Library) to v1.1 | Combined Lead | Monthly — every Phase review
RISK-C-001 | Compliance | GDPR right to deletion conflicts with accounting retention obligations | 3 | 3 | 9 | Soft-delete + anonymisation pattern in data model; ledger entry retained with anonymised token | Engage GDPR-specialist legal advisor if challenged; technical capability built in v1.0 | Combined Lead + Project Sponsor | Before Go-Live
RISK-C-002 | Compliance | Cognia evidence artefacts rejected by reviewers as insufficiently documented | 2 | 4 | 8 | M16 requirements derived from Cognia readiness checklist; Appendix F maps each feature to standard | Evidence export format is config change not rebuild; update template | Project Sponsor | Pre-Go-Live Cognia review
RISK-C-003 | Compliance | Cambridge curriculum structure changes after system built | 2 | 2 | 4 | Grading scale and academic year are admin-configurable; no code change needed | School Admin updates via M20 Settings | School Admin | Annual — each new Cambridge year
RISK-C-004 | Compliance | Pakistan data residency mandate requires student data stored in Pakistan; AWS me-central-1 is UAE | 3 | 4 | 12 | Client legal counsel reviews before Go-Live; AWS architecture supports region migration at infra cost only | If mandate takes effect: delay Go-Live or accept legal risk while migration planned | Project Sponsor + legal counsel | Before Go-Live; annually
RISK-C-005 | Compliance | FERPA compliance gap for US-enrolled students | 2 | 3 | 6 | FERPA requirements in Appendix F; core controls covered by Parent Portal and data export capability | Scope as must-fix before Go-Live if gap found at Appendix F review | Combined Lead | Appendix F review pre-Go-Live
RISK-S-001 | Security | Psychological assessment data exposed to unauthorised roles via visibility rule misconfiguration | 2 | 5 | 10 | BR-031/032 enforced at API response layer; integration tests verify every role-combination | Immediate: offline endpoint; audit log review; notify affected students; patch; re-test | Combined Lead | Pen test (M7) + Phase 4 integration tests
RISK-S-002 | Security | Payment data breach via platform security flaw | 1 | 5 | 5 | Payment card data never stored; Stripe/PayPal tokenise at gateway; platform stores reference token only | Blast radius limited to transaction tokens only; notify users; engage gateway security team | Backend Lead | M08 integration test + pen test (M7)
RISK-S-003 | Security | Credential stuffing attack on student/parent login endpoint | 3 | 3 | 9 | Rate limiting: 5 failed attempts → 15-min lockout; CAPTCHA configurable; breach detection on account creation | Super Admin triggers forced password reset for affected accounts; lower lockout threshold | Combined Lead | Phase 5 pen test
RISK-S-004 | Security | Exam proctoring bypass by student | 3 | 3 | 9 | Multi-layer proctoring: full-screen + tab-switch + webcam + AI behaviour + live proctor dashboard | Manual review workflow: teacher reviews flagged webcam captures regardless of AI flag | Frontend Lead + Combined Lead | Phase 2 M04 acceptance testing
RISK-S-005 | Security | Malicious file upload via assignment submission | 2 | 4 | 8 | Files in S3 with no execute; MIME type validated against magic bytes; ClamAV virus scan on all uploads | Quarantine (not delete) malicious file; flag account; notify teacher; require resubmission | Backend Lead | Integration testing of M03 + M04
RISK-AI-001 | AI-Specific | AI Quiz Service generates question with factually incorrect statement | 3 | 3 | 9 | Part 15.6 AI evaluation: zero critical factual errors gate before UAT; teacher review before students see | Teacher always final gatekeeper; no AI content reaches students without explicit approval | Combined Lead | AI evaluation review before Phase 5 UAT
RISK-AI-002 | AI-Specific | AI Quiz Service prompt injection via teacher-entered syllabus | 2 | 3 | 6 | System prompt not user-controllable; teacher input inserted as structured data field not instruction | Monitor AI response logs for anomalous outputs; temporarily disable if confirmed | Backend Lead | Phase 4 security testing
RISK-AI-003 | AI-Specific | Anthropic API pricing increase raises AI Quiz Service runtime cost | 2 | 2 | 4 | Provider-agnostic LLM proxy: switch to lowest-cost provider via config change | Re-run Part 15.6 evaluation against new provider; switch if criteria met | Backend Lead | Quarterly cost review post-launch
RISK-AI-004 | AI-Specific | AI-assisted dev productivity achieves only 15-20% reduction not 35% assumed | 3 | 4 | 12 | 15% contingency sized for this risk; on-demand outsourced capacity as alternative lever | Engage outsourced capacity funded from contingency; defer M15/M12 to v1.1 if both insufficient | Combined Lead | Phase 2 completion (first real velocity signal)
RISK-AI-005 | AI-Specific | Claude Code / AI coding assistant multi-day outage during critical build phase | 2 | 3 | 6 | AI tooling accelerates delivery but doesn't make build impossible; team can build without it | If outage >5 business days: reassess timeline against pre-AI velocity; invoke RISK-AI-004 contingency | Combined Lead | Weekly during active build
RISK-R-001 | Resource | Combined Lead single point of failure — 4 critical functions in one person | 2 | 5 | 10 | Decision Log current at all times; IaC in code; test cases documented in Appendix E | Engage outsourced senior architect (Part 12.1.1); Project Sponsor assumes PM comms role | Project Sponsor + Combined Lead | Monthly
RISK-R-002 | Resource | Junior Intern attrition mid-project reduces Backend or Frontend capacity by 60% | 3 | 3 | 9 | Intern contracts cover full 20-week build; maintain replacement shortlist | Replace via Part 12.1.1 on-demand capacity; junior from outsourced pool onboards in ~1 week | Combined Lead | Monthly
RISK-R-003 | Resource | Google Stitch exits beta and introduces paid tiers mid-build | 3 | 2 | 6 | Flagged as real risk in Part 13.7; Figma at $20/mo is mature alternative | Adopt Figma immediately; incremental cost absorbed by contingency | UI/UX Designer | At any point during build
RISK-R-004 | Resource | Security Consultant unavailable at planned engagement dates in Phase 5 | 2 | 4 | 8 | Book engagement at Kickoff (M1) — 3-month advance booking for mid-October | Engage second-tier OSCP-certified consultant; brief with pen test scope | Combined Lead | Kickoff (M1, 6 Jul 2026)
RISK-R-005 | Resource | Junior Intern skill gap — does not meet Part 12.4 proficiency criteria on onboarding | 3 | 3 | 9 | Formal coding assessment mandatory before onboarding; not waivable | Replace via Part 12.1.1 on-demand capacity; gap caught in first 2-week sprint | Combined Lead | End of Phase 1 (18 Jul 2026)

## Legend
Risk Score Legend
Score 1-5 | LOW | Accept — monitor at quarterly review
Score 6-11 | MEDIUM | Mitigate — owner takes action
Score 12-25 | HIGH | Critical — immediate mitigation required